## Instructions
		Using the Status tracker

At the end of each week, update the status of all activities completed during the week
The status tracker shown in this worksheet is an example tracker (values filled are during the middle of the week)
Fill in hours spent on each activity during the current week
	If 5 team members each spent an hour, that counts as 5 hours
	Fill in time for activities not fully completed ("ongoing") as well, then update these values during following weeks
During the planning phases, identify the activities to be done during each week
If you spend time on an activity not listed in the tracker, add the activity and list actual hours (need not fill in estimated hours if you didn't estimate it up front)

For new activities, identify the type of activity - documentation, coordination, estimation etc.

At the end of each week, plan ahead for the following week
	Identify people responsible for each activity
	Estimate the hours needed for the activity

PROJECT NUMBER	6
PROJECT NAME	Customized Offers for Mobile Games
PROJECT MENTOR (sponsor)	Mr. Ravi Kiran
TEAM MEMBERS	MNS.Subramanyam
	Adrian Joseph Alva
	Yahnit Sirineni

## Status
PROJECT NUMBER	6
PROJECT NAME	Customized Offers for Mobile Games
PROJECT MENTOR (sponsor)	Mr. Ravi Kiran

Activity Name	Type	Responsible	Estimated Team Hours	Actual Hours	Status	Comments	Estimation error	Estimation error %
See Instructions sheet for usage
Week 1 (August 7- August 13)
Fix meeting with client	Coordination	Yahnit	0.25	0.25	Done	Met with the Client for the first time.	0	0
Client meeting	Coordination	Yahnit	1	1	Done	Understood the area of work of the client.	0	0
Fix meeting with client	Coordination	Subramanyam	0.25	0.25	Done	Fixed time of meeting.	0	0
Introduction to Project	Coordination	Subramanyam	3	1	Done	Understood different mobile games	2	200
Research existing methodology	Preparation	Yahnit	2	1.5	Done	Researched a journal paper related to customized offers.	0.5	33.3333333333
Client meeting	Coordination	Yahnit	1.5	2	Done	Understood the use of google analytics in the project.	-0.5	25
Understanding Google Analytics	Preparation	Subramanyam	2.5	3	Done	Went through analytics data and it’s parameters	-0.5	16.6666666667
Team Meeting	Coordination	Yahnit	1	1	Done	Discussed about the google analytics data.	0	0
Status tracker	Documentation	Subramanyam	0.5	0.5	Done	Completed documenting the week’s work.	0	0
Week 2 (August 14 - August 20)
Team Meeting	Coordination	Subramanyam	1.5	1	Done	Relating analytics data to the project.	0.5	50
Fix meeting with client	Coordination	Yahnit	0.25	0.25	Done	Fixed time of meeting.	0	0
Client meeting	Coordination	Adrian	1	0.75	Done	Had a skype call and discussed analytics data.	0	0
GIT Repository setup	Preparation	Adrian	1	1	Done	Committed project concept document and README.md	0	0
Team Meeting	Preparation	Subramanyam	2	1	Done	Came up with client and server-based solutions for offer triggers	1	100
Team Meeting	Preparation	Yahnit	1	1	Done	Discussed about the offer trigger solutions.	0	0
Fix meeting with client	Coordination	Adrian	0.25	0.25	Done	Fixed time of meeting and skype call.	0	0
Client meeting	Delivery	Subramanyam	1	0.5	Done	Submitted the solutions and discussed the feasibility of the solutions. Gathered the deliverables for next week.	0.5	100
Status tracker	Documentation	Yahnit	0.5	0.5	Done	Completed documenting the week’s work.
Week 3 (August 21 - August 27)
Team Meeting	Preparation	Yahnit	1	1	Done	Discussed different algorithms for offer triggers.	0	0
Pseudo Code Design	Design	Yahnit	3	2	Done	Designed stack based solution for identifying frequent users.
Team Meeting	Preparation	Subramanyam	1	1	Done	Discussed bugs and efficiency of the pseudocode.
Fix meeting with client	Coordination	Subramanyam	0.25	0.25	Done	Fixed time of meeting.	0	0
Client meeting	Delivery	Adrian	1	1	Done	Submitted pseudocode and gathered requirements for improving the algorithm.	0	0
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.
Week 4 (August 28 - September 3)
Team Meeting	Preparation	Subramanyam	2	1.5	Done	Discussed alternate solutions.	0.5	33.3333333333
Alternate Pseudo Code Design	Development	Yahnit	2.5	3.5	Done	Came up with alternate code that includes all corner (test) cases	-1	28.5714285714
Fixed meeting with the client	Coordination	Yahnit	0.25	0.25	Done	Fixed time of skype call
Submitted alternate pseudocode	Delivery	Subramanyam	1	1	Done	Submitted alternate pseudcode on skype (solution approved)
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.
Week 5 (September 4 - September 10)
Team Meeting	Preparation	Subramanyam	1	1	Done	Implementation of pseudocode	0	0
Pseudo Code Implementation	Development	Yahnit	3	4	Done	Python coding	-1	25
Client meeting	Coordination	Adrian	1	1	Done	Discussed python implementation and more ideas for offer triggers	0	0
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.
Week 6 (September 11 – September 17)
Team Meeting	Preparation	Subramanyam	1	1	Done	Discussed making the code more adherent to python standards	0	0
Code updation	Development	Yahnit	2	2	Done	Updated code with standard conventions	0	0
Fix meeting with client	Coordination	Yahnit	0.25	0.25	Done	Fixed time and venue of client meeting	0	0
Client meeting	Coordination	Subramanyam	1	1	Done	Delivered the updated code and received the deliverables for the coming week	0	0
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.	0	0
Week 7 (September 18 – September 24)
Team Meeting	Preparation	Adrian	1	1	Done	Discussed the plan for developing the required deliverables	0	0
Code development	Development	Subramanyam	3	3	Done	Developed the codes for finding users based on attempts, time and money spent	0	0
Fixed meeting with the client	Coordination	Yahnit	0.25	0.25	Done	Fixed time and venue of client meeting	0	0
Updated Project Plan Document	Documentation	Subramanyam	0.5	0.5	Done	Added new entries to milestones
Client meeting	Delivery	Subramanyam	1	1	Done	Delivered the code with all 4 functionalities	0	0
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.
Week 8 (September 25 – October 1)
Documentation of the code	Documentation	Yahnit	1	1	Done	Added documentation to the source code	0	0
Status tracker	Documentation	Subramanyam	0.5	0.5	Done	Completed documenting the week’s work.	0	0
Week 9 (October 2 – October 8)
Team Meeting	Documentation	Adrian	1	1	Done	Discussed the plan for Release 1 presentation	0	0
R1 (video) presentation	Documentation	Subramanyam	1	1	Done	Started work on the R1 presentation	0	0
Final R1 presentation upload	Documentation	Yahnit	3	4	Done	Completed R1 video presentation and uploaded the same.	-1	25
Week 10 (October 9 – October 15)
Team Meeting	Documentation	Yahnit	1	1	Done	Reviwed progress till R1 and discussed future goals.	0	0
Documentation of work till R1	Documentation	Subramanyam	1	1	Done	Updated Test Plan Document and added invidual contributions document	0	0
Status tracker	Delivery	Adrian	0.5	0.5	Done	Completed documenting the week’s work.	0	0
Week 11 (October 16 – October 22)
Fixed meeting with the client	Coordination	Subramanyam	0.25	0.25	Done	Confirmed the time and place of meeting.	0	0
Client meeting	Coordination	Adrian	1	1.5	Done	Explained the details of the event object and database requirements and discussed about python packaging.	-0.5	33.3333333333
Code development	Development	Yahnit	2	2	Done	Studied python packaging and started implementation.	0	0
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.	0	0
Week 12 (October 23 – October 29)
Team Meeting	Preparation	Yahnit	1	1	Done	Discussed the progress on the python packaging implementation.	0	0
Fixed meeting with the client	Coordination	Adrian	0.25	0.25	Done	Confirmed the time and place of meeting.	0	0
Client meeting	Coordination	Subramanyam	1	1.75	Done	Discussed model for offer generation and future milestones	-0.75	42.8571428571
Code development	Development	Subramanyam	2	2	Done	Completed work on packaging the code in python	0	0
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.
Week 13 (October 30 – November 5)
Team Meeting	Development	Adrian	1	1	Done	Worked towards completing the offer generation pipeline(listing the required offer to the particular player)	0	0
Code development	Development	Subramanyam	2	2	Done	Worked on integrating the python code with the javascript code for listing the offer type (store items)	0	0
Client meeting	Coordination	Yahnit	1	1	Done	Discussed the progress of the pipeline and the assumptions about the data given by the client.	0	0
Fixed meeting with the client	Coordination	Adrian	0.25	0.25	Done	Confirmed the time and place of meeting.	0	0
Client meeting	Coordination	Subramanyam	1	1.5	Done	Discussed the progress (completion) of the pipeline and obtained data from the client for offer generation (jungle book game)	-0.5	33.3333333333
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.
Week 14 (November 6 – November 12)
Team Meeting	Development	Subramanyam	1	1	Done	Reviewed full project pipeline and updated documentation	0	0
Code development	Development	Yahnit	2	2	Done	Made minor changes and completed the pipeline.	0	0
Fixed meeting with the client	Coordination	Subramanyam	1	1	Done	Demonstrated the pipeline.	0	0
Code updation	Development	Adrian	1	1	Done	Final review and fix of repository structure, code and documentation	0	0
Release 2 presentatoin	Development	Adrian	4	6	Done	Completed R2 video presentation	-2	33.3333333333
Status tracker	Documentation	Adrian	0.5	0.5	Done	Completed documenting the week’s work.	0	0